Date ............................

UNESCO/Flanders funds-in-trust co-operation Implementation status report

The report is prepared for the review meeting scheduled for 21 December 2006 at Ostend

Project: Secondment of Prof. Willy Bauwens to IHP

Budget code: 513RAB2001

# Sector/Division: UNESCO Cairo Office, Hydrology Programme

Project officer: Dr. Radwan Al-Weshah

Project budget (including programme support costs) US$: 60,500

Implementation period:

original: 2002 - 2006

revised: 2002 - 2007

Date of most recent regular progress report on project: April 2006

Major developments since the most recent progress report:

The project is fully operational. The following missions were carried out with relation to the UNESCO Flanders FUST FRIEND/Nile project:

- Prof. Bauwens attended a comprehensive training workshop on the practical use of the Water Strategy Man (WSM)- Decision Support System (DSS) during the period 26 June – 2 July 2006 in Bologna, Italy. During the training, a number of limitations for the use of the WSM within the Nile basin were identified. Moreover, the framework of the general assemblies and for the training on WSM during the launching workshop of the second phase was defined.

- Prof. Bauwens actively participated in the Launching Workshop of the FRIEND/Nile Second Phase, Cairo, Egypt; 14-19 August 2006. Prof. Bauwens actively participated and contributed to the workshop in general and to the Integrate Water Resources Management (IWRM) sessions in particular. During the workshop, He outlined the 2nd stage of FN and TwinNile to the research team of the project focusing on: expected objectives, structure and framework, expected deliverables,...etc. Prof. Bauwens presented the previous Decision Support Systems in the Nile basin. Moreover, he gave a presentation on the Water Strategy Man model structure and theoretical background.

- 2 -

Special problems to be addressed during the review meeting:

The steering committee and the technical network commission meetings of the Capacity Building and Training on Environmental Planning and Management in Palestine: Phase-II will be held in Sharm El Shiekh, Egypt during the period 3-6 December 2006. Moreover,  a workshop for the FRIEND/Nile: Integrated Water Resources Management (IWRM) will be organized in February 2007 in Uganda. Prof. Bauwens will attend this workshop in his capacity as the IWRM Flemish expert.

Particular observations on the financial situation of the project:

The budget code of this project is valid till end of January 2006.

Recommendation on decisions to be taken during the review meeting:

Extend the project life till end of March 2007 to enable the successful implementation of the project activities and finalizing its related payments.