[file: #Status-SUMAMAD-Phase 2-2.doc/Projects/FUST projects]

Template Narrative Progress Report

for the 17th FUST Steering Committee Meeting, May/June 2010

(date: 7 May 2010)

Project Title: Sustainable Management of Marginal Drylands (SUMAMAD) – Phase 2

Target Country or Region: Africa, Arab States, Asia, Europe, Latin America (Belgium, Bolivia, Burkina Faso, China, Egypt, India, Iran, Jordan, Pakistan, Tunisia)

Budget code: 513/GLO/2017

Contract number:

Funding sources: Flemish Government of Belgium

# Total Budget approved: US$ 1,480,050 (incl. 10% overhead costs)

Reporting Period: September 2009 to May 2010

Executing Agency: UNESCO

Implementing partners: UNESCO Headquarters (Division of Ecological and Earth Sciences and its MAB Programme), in cooperation with the United Nations University – Institute for Water, Environment and Health (UNU-INWEH)

Project starting date: April 2009 (date of project approval)

Project completion date: 31 December 2013

Responsible Sector: UNESCO Science Sector

Name of Persons completing Report: Miguel Clusener-Godt, Division of Ecological and Earth Sciences (SC/EES).

- Summary and Background:

Based on the work already carried out during the first phase of the SUMAMAD Project (2004-2007), the general purpose of the second phase of the project is to conduct research and application-oriented sciences in the following three inter-related fields:

(1) Fostering scientific drylands research:

- Improvement of dryland agriculture (crop and livestock production) through the sustainable use of natural resources focusing on sustainable water conservation and harvesting practices;

- Restoration and rehabilitation of degraded drylands focusing on biodiversity conservation and sustainable use of natural biotic resources.

.

(2) Preparation of policy-relevant guidelines for decision-makers in drylands:

- Developing scenarios for land-use changes (also in the context of climate change) including the assessment of trade-offs and economic valuation of dryland services;

- Interfacing with relevant policy-formulation institutions and processes in the respective countries.

(3) Promoting sustainable livelihoods in drylands:

- Encouraging alternative income-generating activities - diversification of economic options, such as ecotourism, handicraft production, forages, medicinals, dietary diversification, in order to reduce dependencies on traditional dryland agriculture.

A cross-cutting objective is to strengthen capacity-building in all study sites through training schemes on environmental research and conservation, study visits among field project partners, and environmental education in formal and non-formal contexts (such as using the UNESCO Teaching Resource Kit for Dryland Countries).

The following countries, scientific institutions and biosphere reserves are involved in the SUMAMAD Project:

Belgium:	University of Ghent and K.U. Leuven University.

Bolivia:	Universidad Mayor de San Andres, La Paz.

# Burkina Faso:	National Centre for Scientific and Technological Research (CNRST) 			and MAB National Committee.

# China: 	Institute of Botany at the Chinese Academy of Sciences with MAB 				National Committee;

Egypt: 		University of Alexandria and Omayed Biosphere Reserve.

India		Central Arid Zone Research Institute (CAZRI).

I.R. Iran: 	Research Society for Sustainable Rehabilitation of Drylands					(REaSSURED), in collaboration with Fars Research Center for 				Agriculture and Natural Resources (FRCANR).

Jordan: 	Royal Society for the Conservation of Nature (RSCN).

Pakistan: 	Pakistan Council of Research in Water Resources (PCRWR).

Tunisia: 	Institut des Régions Arides de Médenine (IRA).

In addition, the United Nations University – Institute for Water, Environment and Health (UNU-INWEH) collaborates with UNESCO in the implementation of the Project.

Before the first phase of the SUMAMAD Project was approved for funding by the Flemish Government of Belgium in spring 2004, several preparatory meetings/workshops were held. Moreover, the following international SUMAMAD Project Workshops have been organized as follows:

(1)	May 2002: Project Preparatory Meeting held at UNESCO Headquarters (Paris, France) with UNESCO, UNU and ICARDA; this meeting resulted in the selection of project sites and scientific partner institutions in the participating countries.

(2)	September 2002: The First International Workshop on “Sustainable Management of Marginal Drylands – Application of Indigenous Knowledge for Coastal Drylands” held in Cairo and Alexandria (Egypt). The workshop was also attended by Belgian scientists from K.U. Leuven and Ghent University. The proceedings were published by UNU (UNU Desertification Series No. 5).

(3) 	February 2003: Project working meeting among UNESCO, UNU and ICARDA at the 3rd World Water Conference in Kyoto (Japan). At this meeting it was decided that – in order to keep the “project momentum” until extra-budgetary support was secured by the Flemish Government of Belgium - UNU provides grants to the SUMAMAD Project countries in 2003 to carry out research work and to make site-specific project assessments, and that UNESCO funds and organizes the first SUMAMAD Project Workshop in Iran later in the year.

(4) 	November/December 2003: The Second International Project Workshop on Sustainable Management of Marginal Drylands (SUMAMAD) was held in Shiraz (Iran) with all project partners including Belgian scientists and a representative of the Belgian Government of Flanders. SUMAMAD countries presented their site-specific assessment reports. The proceedings were published by UNESCO (UNESCO-MAB Drylands Series No. 3).

(5) 	December 2004: The Third International Project Workshop on Sustainable 	Management of Marginal Drylands (SUMAMAD) was held in Djerba (Tunisia) 	in 	collaboration with the Institut des Régions Arides (IRA) and included a 	field trip to 	various project related sites in Medenine area. The workshop proceedings have been 	published by UNESCO in October 2005. Unfortunately, the SUMAMAD project 	partner from Pakistan was not able to attend the workshop due to visa problems.

(6)	Originally scheduled for November 2005, the Fourth International Project Workshop 	had to be postponed to 2006 due to the devastating earthquake that affected the 	country in early October 2005. Accordingly, the Fourth International Project 	Workshop on Sustainable Management of Marginal Drylands (SUMAMAD) took 	place in Islamabad (Pakistan) in collaboration with Pakistan Council for Research into 	Water Resources (PCRWR) 	and included a field trip to Cholistan desert and to Lal 	Suhanra Biosphere Reserve. 	Unfortunately, the two Chinese project partners and the 	Uzbek project partner were unable to attend due to illness. Moreover, the Iranian 	project partner could not attend due to passport/visa problems. The workshop 	proceedings have been published by PCRWR and are also available in pdf format on 	the SUMAMAD website at 	http://unesdoc.unesco.org/images/0014/001473/147306E.pdf .

(7) 	The Fifth International Project Workshop has been held in Aleppo (Syria) from 13 to 16 November 2006, and was hosted by ICARDA. With the exception of the Belgian and Pakistani SUMAMAD partners, representatives from all other project sites attended the meeting. The workshop proceedings have been printed and distributed.

(8) 	The Sixth International Project Workshop has been held in Xilinhot City and Zenglan Banner (China) from 6 to 12 September 2007 and was hosted by Prof Jiang Gaoming of the Chinese Academy of Sciences. All SUMAMAD team leaders were present. A field trip was organized to the Xilingol Biosphere Reserve and to the Hunshandake sandlands area. No workshop proceedings emanated from this workshop, as the final SUMAMAD Publication (available at http://unesdoc.unesco.org/images/0016/001609/160924E.pdf) summarized project results since the start of the project.

- Description of project activities undertaken during the reporting period

Activities carried out from September 2009 to May 2010:

- UNESCO Headquarters, in collaboration with the UNESCO-New Delhi Office and India’s Central Arid Zone Research Institute (CAZRI), organized the 7th international SUMAMAD Project Workshop in Jodhpur, Rajasthan (India) from 22 – 23 November 2009. With the exception of the Jordanian and Pakistani SUMAMAD partners, representatives from all other project sites attended the meeting.  This workshop was held in conjunction with CAZRI’s international conference on “Nurturing Arid Zones for People and The Environment: Issues and Agenda for the 21st Century” which was held in Jodhpur from 24 – 28 November 2009 so that SUMAMAD project scientists could attend the CAZRI conference.  Workshop proceedings were not published, as the workshop was held shortly after the launch of project phase 2, and project partners did not feel that there were sufficient results to justify a publication at this stage.

- SUMAMAD information was uploaded to the new UNESCO/Flanders Funds-in-Trust website (UNESCO; see:  http://fust.iode.org/index.php/ecology)

- Workplans for 2010 have been prepared for all project sites and are awaiting the arrival of funding.

- Difficulties and Problems encountered and measures taken, any changes in implementation

The late arrival of funding has delayed the start of some planned activities for 2010.  It is hoped that funding will arrive during May 2010 and project activities will be able to move forward without substantial need for modifications.

- Project Results achieved during the reporting period

See Section II above.

- Lessons learned and Sustainability

The project is deemed sustainable as all project partners are embedded in university or other research institutional settings that will continue beyond the ending of the SUMAMAD Project. Hence, research results will be utilized on a long-term basis.

- Evaluation recommendations when applicable

The final report and publication of the SUMAMAD-2 Project Phase will contain a number of site-specific recommendations as well as overall recommendations to improve the sustainable development of drylands at large.

- Visibility: describe any  visibility action implemented during the reporting period

SUMAMAD information was uploaded to the new UNESCO/Flanders Funds-in-Trust website (UNESCO; see:  http://fust.iode.org/index.php/ecology), which will serve to increase project visibility.  The linking of SUMAMAD workshops to other major events, such as the CAZRI conference in Jodhpur in 2009 and the upcoming biodiversity conference in Alexandria (Egypt) in 2010, will likewise enhance project visibility.

- Work plan for the following period (please complete the attached table and when applicable add an eventual budget revision)

See Annual Workplan and Table with SUMAMAD 2010 Activities below.

- Annexes (publications , reports and other project outputs, when applicable)

Seventh International SUMAMAD Project Workshop Report.

#### Annual Workplan

Project Code and Title: 513/GLO/2017 "SUMAMAD-2 Project"                                                                                                                    Year: 2010

| Planned Activities | Expected Outputs | Timeframe From To | Responsible Party |
| --- | --- | --- | --- |
| Field research activities and national information/training seminars at national field project levels | Reports to be presented at 8th international SUMAMAD workshop (Alexandria, Nov. 2010) | Jan. 2010 | Dec. 2010 | UNESCO, UNU-INWEH and team leaders of national projects |
| Organization of 8th international SUMAMAD Project workshop in Alexandria (Egypt) in Nov. 2010 | Discussion of SUMAMAD project results and direction now that phase 2 of the project is well underway. | July 2010 | Nov. 2010 | UNESCO Headquarters, University of Alexandria, Omayed Biosphere Reserve |

Table: Detailed Work plans of SUMAMAD 2010 study sites

SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS

Project Workplan for 2010

Country: Bolivia

| Goal/Overall Objective: Building the capacity of dryland researchers to transfer their scientific findings for use both by local communities and for policy-level decision-making |
| --- |
| Objectives | Field Research activities | Estimated budget USD | Remarks |
| Fostering scientific drylands research | 1.Evaluation of Nitrogen mineralization rates for soil amendments under deficit irrigation soils in the Bolivian Highlands 2.Agroclimatic description and climate change trends 3.Remote sensing evaluation of evapotranspiration in the Bolivian Highlands as indicator of climate change | 8000 | -- |
| Preparation of policy-relevant guidelines for decision-makers in drylands | 1.Evaluation of climatic indicators for decision making in the Bolivian highlands 2.Evaluation of the socioeconomic dynamics of quinoa producers in the area 3.Guidelines for adequate use of soil amendments for quinoa production in the Bolivian Highlands | 8000 | -- |
| Promoting sustainable livelihoods in drylands | 1. Management of different soil amendments to promote sustainable farming systems in the study area. 2.Evaluation of market insertion of quinoa producers of the study area | 5350 | -- |
| National seminar | 1.To be defined | 2000 | -- |

SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS

Project Workplan for 2010

Country: BURKINA FASO

| Goal/Overall Objective: Building the capacity of dryland researchers to transfer their scientific findings for use both by local communities and for policy-level decision-making |
| --- |
| Objectives | Field Research activities | Estimated budget | Remarks |
| Fostering scientific drylands research | 1. Evaluation of land use practices including the local viable know-how: selection, motoring and evaluation 2. Establishing experimental sites for demonstrations: conception and testing | 2 500 3 500 |  |
| Preparation of policy-relevant guidelines for decision-makers in drylands | 1. Interfacing with relevant policy-formulation institutions (CNRST, OFINAP, CN) and processes in the respective countries.. 2. Building the scientific, technical capacities of the stakeholders (AGEREF) 3. Developing computer science tools (data, WEB site, SIG) and documenting of climate change | 2 000 3 500 3 500 | CNRST and MAB Committee Financing : 2 000 |
| Promoting sustainable livelihoods in drylands | 1. Better organising and implementing the poverty control sustainable local initiatives; 2. Increasing local community’s professionalism in natural resources management. . | 3 000 4 000 |  |
| National seminar | 1. Participants expenses 2. Local travel expenses 3. Meal and drinking costs 4. Supplies (papers, ballpoint pen) 5. Communication expenses | 1 500 1 000 800 700 1 000 | CNRST and MAB Committee Financing: 3 000 |
|  | Total | 27 000 | 5 000 |

SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS

Project Workplan for 2010

Country: China

Goal/Overall Objective: Building the capacity of dryland researchers to transfer their scientific findings for use both by local communities and for policy-level decision-making In 2010, a comparative study is planned on economic output and ecological impact of chicken farming versus traditional grazing in Hunshandake project site. Also foreseen are studies on plant and water conservation practices, especially the response of plant community to changing of underground water. In order to find out the scientific mechanism towards saving grain and protecting grassland through chicken farming in grassland, chemical analysis will be performed on plant and insect samples from the sandland ecosystem. Alternative income-generating activities including chicken farming, traditional Toufu production, dairy industry, especially the totally new green house vegetable production using chicken little and or cattle manure will be continued or tested. Those activities together will help to reduce dependencies on traditional grassland pasture. A national seminar based on achievements of the project will be sponsored and organized by the project team. Deep discussion will be conducted on the potential of promotion of livelihoods through organic chicken farming, dairy production, and greenhouse vegetables; Improvement of sandland pasture through “replacing mammals with birds” in the grassland and the sustainable use of water and space resources; Developing scenarios for land-use changes including the assessment of trade-offs and economic valuation of dryland services. Policy-relevant guidelines for decision-makers in China’s sandland ecosystem management will be prepared.

| Objectives | Field Research activities | Estimated budget | Remarks |
| --- | --- | --- | --- |
| Fostering scientific drylands research | 1. Study on the response of plant communities to underground water levels (UWL); 2. Biodiversity and primary production response to UWL; 3. Study on the convert effect from grain to meat in Chicken under grassland conditions; 4. Chemical analysis on the natural food (leaves, insects and seeds) for Chicken. | 13000 USD | Field experiment: 10000 USD; Chemical Analysis: 3000USD |
| Preparation of policy-relevant guidelines for decision-makers in sandland areas of China | 1. Comparative study on the economic and ecological output between chicken farming and traditional grazing; 2. Experimental data collection on chicken farming and free grazing; 3. Interviewing with local famers, the business company and local governors; 4. Reporting to the high officials; 5. Publishing related articles in newspapers or other medias. | 2000 USD | Expert fee: 1000 USD; Social study: 1000 USD |
| Promoting sustainable livelihoods in drylands | 1. Production of organic chicken farming and exploring market in cities; 2. Dairy cattle raising and milk Toufu production and selling; 3. Green house in the project site will be built to grow vegetables using the organic fertilizers from chicken and cattle. | 5000 USD | Demonstrative Green house: 3000 USD Organic chicken farming: 2000 USD |
| National seminar | 1. Scenario building as policy making tools; 2. Shift of land use pattern in order to promote both the ecological and economic output; 3. Carbon sequestration potentials if the grassland is properly protected; 4.Bidiversity changes in grassland and the problems related with chicken farming; 5. Water resource utilization especially underground water and snow. | 2000 USD for National seminar | Zhenglan Banner or the project team will cover some budge |

SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS

Project Workplan for 2010

Country:  Egypt

| Goal/Overall Objective: Building the capacity of dryland researchers to transfer their scientific findings for use both by local communities and for policy-level decision-making |
| --- |
| Objectives | Field Research activities | Estimated budget | Remarks |
| Fostering scientific drylands research | Monitoring research on land transformations including field surveys, questionnaires, socioeconomic studies. Assessing the effect of summer resorts on the local market analysis Assessing the deterioration of goods and services, of OBR particularly water resources | 4000 2000 |  |
| Preparation of policy-relevant guidelines for decision-makers in drylands | preparing a policy brief (in Arabic ) on the effect of climate change on the local environment Preparing a guideline on a model management plan Site selection of new core areas to be declared in the OBR.2. | 3000 2000 1000 |  |
| Promoting sustainable livelihoods in drylands | provision of income generating activity for women: handicraft material provision of high productive olive propagules for oli and olive production for men | 4000 4000 |  |
| National seminar | 1.organizing a national workshop for spreading out the findings of the results of the current phase of the project 2. organizing meetings with the local stake holders, city and village councils. | 1500 500 |  |

| Goal/Overall Objective: Building the capacity of dry land researchers to transfer their scientific findings for use both by local communities and for policy-level decision-making |
| --- |
| Objectives | Field Research activities | Est. budget (Rs.x 105) | Remarks |
| 1. Fostering scientific dry lands research | 1. Execution of rangeland and runoff farming systems activities (Less than 200 mm rainfall) Improvement and efficient management of rangeland, runoff harvesting and animal nutrition based activities through collective decision of stakeholders 2. Execution of crop diversification activities(200-400 mm rainfall) Introduction of crop diversification and alternate land use systems, Efficient management of rainwater Livestock production with improved management practices 3. Recruitment of JRF, field supervisor and contractual labour services | 6.00 8.50 3.00 | Estimated budget includes Experimental expenses Traveling charges Purchase of equipments. Miscellaneous items Needed for conducting field and associated activities |
| 2. Preparation of policy-relevant guidelines for decision-makers in dry lands | Scenario building for rangeland activities in the context of climate change Development of sustainable farming system modules and feedback analysis for future policy decisions |  |  |
| 3. Promoting sustainable livelihoods in dry lands | Improvement in rural livelihood through alternate income generation activities Training programmes for agro-based and traditional craft-based entrepreneurship Income generation through crop diversification and value addition | 0.50 |  |
| 4. National seminar | Organization of one National Seminar | 1.00 | Interaction with researchers and policy makers |
| SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS Project Work plan for 2010 |
| Country: India (CAZRI, Jodhpur) |

SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS

Project Workplan for 2010

Country:  Iran

| 2010 year (USD) | Identification of items | Activities | SUMAMD broad objectives |
| --- | --- | --- | --- |
| FRCANR & REaSSUTED | SUMAMAD | Amount |  |  |  |
| 0 | 6,000 | 6,000 | Insertion the sensors of TDR, providing the SAP flow meter, monitoring, surveying, transportation, perdiem & salary | 1- Efficiency of flood water spreading on net recharge of the aquifer | Scientific studies |
| 0 | 600 | 600 | Monitoring, transportation, perdiem & salary | 2- Jojoba trial |  |
| 0 | 1,200 | 1,200 | Vegetation measurements, species identification, transportation, perdiem & salary | 3- Biodiversity study |  |
| 0 | 2400 | 2400 | GC/mass spectrometry, identification of organisms, transportation, perdiem & salary | 4- Sow bug study |  |
| 1,313000 | 0 | 1313000 | Construction and maintenance of FWS, transportation, perdiem & salary | 5- Construction of FWS and green village |  |
| 0 | 4000 | 4000 | Relationship with people, analysis of the present situation, education and extension, transportation, perdiem & salary | 1- Empowerment of the cooperatives | Policy-relevant analyses |
| 2000 | 2000 | 4000 | Advertisements, announcement, executives, , transportation, perdiem & salary | 2- National workshops |  |
| 0 | 1,000 | 1,000 | Cultivation, maintenance and harvesting of barley, education and extension, , transportation, perdiem & salary | 1- Spate irrigated barley (Toropy variety) trial | Sustainable livelihoods |
| 0 | 4000 | 4000 | Maintenance, disease protection, adaptation to the dry condition, analysis of the honey, transportation, perdiem & salary | 2- Honey production |  |
| 0 | 8000 | 8000 | Study on potential income generation alternatives with participatory approach, economic and sociologic analysis, transportation, perdiem & salary | 3- Socio-economic analysis of income generative alternatives in the Gareh Bygone Plain |  |
| 1315000 | 29200 | 1344200 | Total |

Country: Jordan

| Objectives | Year 2 | 2010Budget US |
| --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 |  |
| Objective 1: | Prepare and implement a comprehensive baseline livestock and rangeland use survey | SUMAMAD | RSCN |
| Prepare a comprehensive grazing management plan for Al-barrah area based on the collected information in the past year. |  |  |  |  | 10000 | 2000 |
| Help the stockowners to establish a specialized cooperative to organize them and to ease the work with them. |  |  |  |  | 4000 | 1000 |
| Hold a technical workshop with the stockowners for exchange rangeland study information with the problems and expected solutions. |  |  |  |  | 1500 | 1000 |

| Objectives | Year 2 | 2010Budget US |
| --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 |  |
| Objective 2: | To review relevant literature on participatory approach and accessibility to community. | SUMAMAD | RSCN |
| Review current and previous studies in participatory approaches in Jordan |  |  |  |  | 1000 | 1000 |
| Document and disseminate lesson learned on these approaches |  |  |  |  | 1000 | 1000 |
| Determine and select the most appropriate approach to be used in Barra area |  |  |  |  | 500 | 500 |
| Hold a technical workshop for exchange experience and information |  |  |  |  | 2000 | 500 |

| Objectives | Q1 | Q2 | Q3 | Q4 | 2010Budget US |
| --- | --- | --- | --- | --- | --- |
| Objective 3: | To characterize pastoral communities using the resources of Al Bara area in DBR | SUMAMAD | RSCN |
| Determine total population of grazing animals. |  |  |  |  | 500 | 500 |
| Determine number of flocks per households |  |  |  |  | 500 | 500 |
| Assess flock composition and structure |  |  |  |  | 500 | 500 |
| Determine the social and economic network and prepare a profile |  |  |  |  | 500 | 500 |

The Total Budget for 2010 from the SUMAMAD = (22000) US Dollar.

SUSTAINABLE MANAGEMENT OF MARGINAL DRYLANDS

Project Workplan for 2010

Country: Pakistan

| Goal/Overall Objective: Building the capacity of dryland researchers to transfer their scientific findings for use both by local communities and for policy- level decision-making. |
| --- |
| Objectives | Field Research Activities | Estimated budget (US $) | Remarks |
| Fostering scientific dryland research, | Rehabilitation of degraded rangelands in Cholistan desert by using local resources (water, land and vegetation). Introduction of controlled grazing system (fencing of the area). Management strategies for enhancement of canopy cover and biomass production (reseeding of grasses and irrigation supplement). | 12000.00 | The expenditure of objective include; extension of fencing of the area, irrigation system and reseeding. |
| Preparation of policy-relevant guidelines for decision-makers in drylands, | Introduction of Resource Conservation Technology (RCT) which include use of High Efficiency Irrigation for rangelands development. Mass awareness for adopting controlled grazing system. Constitution of Rangelands Decision - Making Forum for welfare and rational use of rangelands; taking concerned departments (Cholistan Development Authority, PCRWR, Forest department) and end users on board. | 7000.00 | Expenditure of the objective include; operation & maintenance of irrigation system, petroleum, transport charges, TADA of experts etc. |
| Promoting sustainable livelihoods in drylands, | Enhancement of forage for sustainable livestock growth and production. Exhibition of local products (livestock byproducts, local embroidery and weaving). | 1000.00 | Support of local people for livelihood activities. The expenditure was not included in initial cost of the proposal from Pakistan side, but it will be managed from approved funds. |
| National Seminar. | Capacity building of local people through lectures, demonstration videos and pictures for adapting identified management strategies for sustainable use of rangelands. Documentation of ideas/ problems of community for Decision- makers/ planners of future projects. | 2000.00 |  |
|  | Total US Dollars | 22000.00 |  |

Country: Tunisia

Study site

Watershed of Zeuss-Koutine and Bouhedma biosphere reserve, Tunisia

Partner institution

Institut des Régions Arides (IRA)

Name and full address of National Project Coordinator

Dr Mohamed OUESSAR

4119 El Fjè – Medenine – TUNISIA

Phone : + 216 75 633 005     Fax: + 216 75 633 006

Email : Med.Ouessar@ira.agrinet.tn

Name and full address of National Project Coordinator Deputy

Dr Houcine TAAMALLAH

4119 El Fjè – Medenine – TUNISIA

Phone : + 216 75 633 005/647     Fax: + 216 75 633 006

Email : Taamallah.Houcine@ira.rnrt.tn

2. Major objectives

The main objectives to be targeted are:

- Combating desertification and improvement of dryland agriculture in the context of climate changes (CC),

- Development of decision making tools for land use management,

- Promotion of alternative income generating sources for local communities.

3. Scientific/research studies

For the year 2010, the scientific/research studies will focus on:

- Groundwater recharge structures

- Exploitation of margines

- Impacts of Acacia plantations

- Decision making tool

3.1. Groundwater recharge techniques

In the framework of the implementation of the national strategy for soil conservation and since 1990, numerous groundwater recharge structures (gabion check dams and recharge wells) have been installed to mobilize the runoff water for the replenishment of the underneath aquifers. Previous studies (Yahyaoui & Ouessar, 2000; Ouessar, 2007) showed that short term effects are positive but long term impacts need to be investigated. Therefore, the aim of this study is to assess the performance of those structures. The work will be conducted in the watershed of wadi Hallouf (Medenine). It will consist of:

- Implementation of the second part of the surveys started last year (2009),

- Collection of additional information: piezometric levels, rainfall data, runoff events, etc.

- Analysis of the collected data.

3.2. Exploitation of margines

Because of its harmful effects on the environment (pollution, biotope destruction, etc) and the corrosion and blocking of the sewage pipes, the disposal of margines (olive waste water) in the public wastewater discharge network or in nature (water courses, etc.) is strictly prohibited and the owners of olive manufactures are obliged to store it in individual or grouped ponds (ONAS, 1997). However, this solution is only provisional considering the increase in produced quantities of margines and risks of infiltration. The alternative solutions are: direct spreading in the olive groves or its use as fertilizer and stabilizing material in the grazing lands to control win erosion. The work conducted by Taamallah (2007), and which consisted of spreading of margine in the inter-row area between the olive trees lines in the state owned olive orchard in Chammakh (Zarzis, South east Tunisia), showed that positive physical and chemical improvements of the soils could be obtained.

This study will explore the exploitation of margine on irrigated soils using 200 m3/ha. The activities to be carried out will focus on:

- kinetic of organic carbon biodegradation and nitrogen biodegradation,

- Regular monitoring of: soil water content, salinity, NPK, and crop development.

3.3. Ecological impacts of Acacia plantations

In the framework of the UNFCC and Kyoto protocol, the Government of Flanders (Belgium) is supporting the Central Forest Service of the Ministry of Agriculture to extend the plantation of Acacia radiana in its origin region in the National park of Bouhedma classified also as UNESCO Biosphere reserve.

The objectives of the proposed research work are to assess the influence of afforestation on soil properties and microclimate. This was started last year and it will be continued during this year (2010). The team will focus:

- Monitoring of climate through the data collected by the already installed weather station in the main building (Borj) of the park,

- Analysis of the collected soil data (water content, infiltration, temperature, etc)

- Exploration of the use of remote sensing data.

3.4. Decision making tool

In the frame of the implementation of the national action plan (NAP) as part of the UNCCD, a network of observatories for the assessment and monitoring of desertification has been set covering the main agro-ecological zones of Tunisia. Jefffara represents one of the main observatories in a typical arid zone threatened by desertification. It was chosen and certified as ROSELT/OSS site. This site is part also of the arid zones observatory implemented by IRA in the frame of the national monitoring system of desertification coordinated by the national focal point of the UNCCD. It is in this framework that the GIS based model LEIS (Local Environmental Information System) (in French known as SIEL) will be applied to this observatory. The focus will be made on:

- Preparation of input data: remotely sensed data (satellite images), field measurements (vegetation biomass, yields, GPS, etc.), and socio-economic surveys (households, income, activities, etc.).

- Integration into the GIS environment (ArcGIS),

- Running multiple scenarios to assess the impacts of changing one or many parameters (population, drought recurrence, livestock, wood consumption, etc.) using participatory approach.

4. Promoting alternative livelihood

The local cooperating NGOs are conducting various alternative income generation activities. For this year, the project will assist them by consolidating some already engaged programs. It will concern mainly the exploitation of medical and aromatic plants.

5. Budget breakdown

The budget* breakdown of the year 2010 is given in the following table.

| Goal/Overall Objective: Building the capacity of dryland researchers to transfer their scientific findings for use both by local communities and for policy-level decision-making |
| --- |
| Objectives | Field Research activities | Estimated budget* | Remarks |
| Fostering scientific drylands research | Recharge well Margine exploitation Ecological impacts | 3000 4000 6000 |  |
| Preparation of policy-relevant guidelines for decision-makers in drylands | Decision making tool | 3000 |  |
| Promoting sustainable livelihoods in drylands | Alternative income generation | 4000 |  |
| National seminar | Organization | 2000 |  |

* As it was the case during phase 1, the budget will be administered by ICARDA office in Tunis.

6. Team

A multidisciplinary and cross institutions team will be involved. The main investigators are:

| Name | Expertise | Institution |
| --- | --- | --- |
| Research sub-team: |  |  |
| Houcine KHATTELI | Desertification | IRA |
| Mohamed OUESSAR | Water harvesting | IRA, Coordinator |
| Houcine TAAMALLAH | Soil Science | IRA |
| Mongi SGHAIER | Agro-socio-economy | IRA |
| Azaiez Ouled Belgacem | Rangeland ecology | IRA |
| Donald Gabriels | Soil conservation | UG |
| Robert De Wulf | Remote sensing | UG |
| Koen De Smet | Biodiversity | GF |
| Mounir ABICHOU | Agronomy | IO |
| With the active collaboration of: |  |  |
| Development sub-team: |  |  |
| Messaoud BGHIR | Agronomy | CRDA |
| Lazhar Hamdi | Biodiversity | Biosphere Reserve |
| NGO sub-team: |  |  |
| Ahmed EL ABED | - | APB |
| Faical ZAMMOURI | - | AJZ |

IO: Institut d’Olivier (Direction de Zarzis) (Olive Research Institute – Zarzis division), CRDA: Commissariat Regional au Développement Agricole de Médenine (Regional department of the Ministry of Agriculture); APB: Association de Sauvegarde de la Biodiversité à Béni Khédache; AJZ: Association des Jeunes de Zammour à Béni Khédache, GDA : Groupement de Développement Agricole, UG: University of Ghent (Belgium); GF: Government of Flanders (Belgium).